## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Setup Java project structure and database connection | MUST HAVE | NA | Sanskar Jadhav | 3- Completed
Sprint 1 | Sprint 1 | US-02 | Create account signup and login module | MUST HAVE | US-01 | Sanskar Jadhav | 3- Completed
Sprint 2 | Sprint 2 | US-03 | Implement deposit functionality | MUST HAVE | US-02 | Sanskar Jadhav | 3- Completed
Sprint 2 | Sprint 2 | US-04 | Implement withdrawal functionality | MUST HAVE | US-03 | Sanskar Jadhav | 3- Completed
Sprint 2 | Sprint 2 | US-05 | Add balance inquiry feature | MUST HAVE | US-02 | Sanskar Jadhav | 3- Completed
Sprint 3 | Sprint 3 | US-06 | Add fast cash transaction feature | SHOULD HAVE | US-03 | Sanskar Jadhav | 3- Completed
Sprint 3 | Sprint 3 | US-07 | Implement PIN change module | SHOULD HAVE | US-02 | Sanskar Jadhav | 3- Completed
Sprint 3 | Sprint 3 | US-08 | Add mini statement / transaction history | SHOULD HAVE | US-03 | Sanskar Jadhav | 3- Completed
Sprint 4 | Sprint 4 | US-09 | Design Java Swing ATM UI screens | COULD HAVE | US-02 | Sanskar Jadhav | 3- Completed
Sprint 4 | Sprint 4 | US-10 | Perform end-to-end testing and bug fixing | MUST HAVE | US-09 | Sanskar Jadhav | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7